## Summry
Theseus_VX
Engineer name: | Eliran Balas
CIR Name (Placed on Rack label): | Quartet_VantageX
Project Name: | Quartet_Phase_#3
Last Manual Revision Number | 527049_5, 526733_4, 527055_3
Date | 2020-07-02
Main Sections
1. Check List
2. Physical Servers Installation
4. Task & Open issue
1.HO Meeting

## Server_Configuration
Validation | Server_Template
Domain | .test.com
Physical servers Istallation
[8 empty] | iDrac Basic Seetings | [7 empty] | Virtual Disk 0 |  | Virtual Disk 1 |  | Configuration |  |  |  | OS | [8 empty] | OS Installation | [9 empty] | Per
# | Enable Config | Site | Site # | Server Type | CIR Name | Server Name | Service TAG | DHCP IP | IP | SM | DG | Boot Mode | Virtual Console | Time Zone | Boot Seq | Raid Layout #1 | Disks # | Raid Layout #2 | Disks #2 | IP's | Virtual Disk 0 | Virtual Disk 1 | iDrac_Clear | Ip Addr | SM2 | DG | NTP | Resolv | Network Interface | Second Network Interface | Network Interface Type | OS version | Column9 | Column92 | IP Addr | HostName | Partition | Domain | NTP10 | License | Validation | Team 0 | Team 1 | Team 2 | Team 3 | Team 4 | Team 5 | Team 6 | Team 7 | Team 8
1 | TRUE |  |  | ESXi | ESX | ESX |  | 192.168.0.131 | 192.168.0.131 | 255.255.255.0 | 192.168.0.245 | Bios | java | UTC | N/A | #N/A | #N/A | N/A | N/A | FALSE | FALSE | FALSE | FALSE | 1.1.1.1 | 255.255.255.0 | 1.1.1.2 | 8.8.8.8 | 8.8.8.8 | vmnic0 | vmnic1 | team | ESXi6.5
1 | TRUE |  |  | ESXi | ESX | ESX |  | 192.168.0.133 | 192.168.0.133 | 255.255.255.0 | 192.168.0.245 | Bios | java | UTC | N/A | #N/A | #N/A | N/A | N/A | FALSE | FALSE | FALSE | FALSE | 2.2.2.2 | 255.255.255.0 | 2.2.2.3 | 8.8.8.8 | 8.8.8.8 | vmnic0 | vmnic1 | team | ESXi6.5
1 | TRUE |  |  | ESXi | ESX | ESX |  | 192.168.0.132 | 192.168.0.132 | 255.255.255.0 | 192.168.0.245 | Bios | java | UTC | N/A | #N/A | #N/A | N/A | N/A | FALSE | FALSE | FALSE | FALSE | 3.3.3.3 | 255.255.255.0 | 3.3.3.4 | 8.8.8.8 | 8.8.8.8 | vmnic0 | vmnic1 | team | ESXi6.5

## Server_Template
Server Type | SM | DG | Boot Mode | Virtual Console | Time Zone | Boot Seq | Raid Layout #1 | Disks # | Raid Layout #2 | Disks #2 | Enable Config | IP's | Virtual Disk 0 | Virtual Disk 1 | iDrac_Clear
SAU | 255.255.255.0 | 172.29.91.254 | Bios | java | UTC |  | 1 | 2 |  |  | FALSE | TRUE | TRUE | FALSE | TRUE
SAU # A | 255.255.255.0 | 172.29.91.254 | Bios | java | UTC |  | 1 | 2 |  |  | TRUE | FALSE | FALSE | FALSE | TRUE
Worker | 255.255.255.0 | 192.168.100.245 | Bios | java | UTC |  | 1 | 2 |  |  | TRUE | FALSE | TRUE | FALSE
Kafka | 255.255.255.0 | 192.168.100.245 | Bios | java | UTC |  | 1 | 2 | 10 | 6 | TRUE | FALSE | TRUE | TRUE
ESXi | 255.255.255.0 | 192.168.0.245 | Bios | java | UTC |  | N/A | N/A |  |  | TRUE | TRUE | FALSE | FALSE | TRUE

## Check List
# | Step Description | Status | comment
1 | Verify Wiring and cabling has been done
Phisical - Installation & Configuration #BE
1 | ESX
Phisical - Installation & Configuration #FE UZ Mobile
1 | MDE Servers
2 | SAU Servers x
3 | TBoS Servers
Phisical - Installation & Configuration #FE Ucell
1 | MDE Servers
2 | SAU Servers
3 | TBoS Servers
Phisical - Installation & Configuration #FE UMS
1 | MDE Servers
2 | SAU Servers
3 | TBoS Servers

## Task & Open issue
Task & Open Issues \ changed Configuration
# | Date | Open By | Status | Server /Equipment | Description | Root cause | Generic\specific
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35

## HO Meeting
HO Meeting
Engineer name: Eliran Balas
SI name :
# | Virtual Environment review | Status | Remarks
1 | Review VIM validator XML to see all Virtual Machines names & OS & Specs & SEP &Activation.
2 | Review Cluster and Hosts configurations (Network, HA, storage, ESX & vCenter licenses)
3 | Make sure no alerts on the system
Storage Overview
4 | Review storage physical configuration (controller, shelves, aggr, etc.)
5 | Review Volumes configurations.
6 | Review storage Cluster and SVMs configurations.
Review “Infra Validation” folders and reports
7 | SEPM
8 | WSUS
9 | NTP
10 | GPO's
11 | Netapp installation
SAU2 1
SAU2 2
SAU2 3
SAU2 4
SAU2 5
SAU2 6
SAU2 7
SAU2 8
SAU2 9
SAU2 10
SAU2 11
SAU2 12
SAU2 13
SAU2 14
SAU2 15
SAU2 16
SAU2 17

## Validation
Country & RCity | מס' מכשיר |  | Boot Mode | Virtual Console | Time Zone | Boot Seq | Raid Layout #1 | Disks #
SAU2 13 | 9YPWD53 | TRUE | Bios | java | UTC |  | 1 | 1
SAU2 4 | FYPWD53 | FALSE | Uefi | HTML5 |  |  | 5 | 2
SAU2 14 | G58CH73 | [5 empty] | 6 | 3
SAU2 15 | 468CH73 | [5 empty] | 10 | 4
SAU2 5 | J58CH73 | [6 empty] | 5
SAU2 6 | H58CH73 | [6 empty] | 6
SAU2 16 | 168CH73 | [6 empty] | 7
SAU2 17 | GYPWD53 | [6 empty] | 8
SAU2 7 | 368CH73 | [6 empty] | 9
SAU2 8 | 378CH73 | [6 empty] | 10
SAU2 9 | D58CH73 | [6 empty] | 11
SAU2 1 | JYPWD53 | [6 empty] | 12
SAU2 10 | HYPWD53 | [6 empty] | 13
SAU2 2 | F58CH73 | [6 empty] | 14
SAU2 3 | 268CH73 | [6 empty] | 15
SAU2 11 | J68CH73 | [6 empty] | 16
SAU2 12 | 568CH73 | [6 empty] | Reset
OLD
[9 empty] | SAU2 13 | 9YPWD53
[9 empty] | SAU2 4 | FYPWD53
[9 empty] | SAU2 14 | G58CH73
[9 empty] | SAU2 15 | 468CH73
[9 empty] | SAU2 5 | J58CH73
[9 empty] | SAU2 6 | H58CH73
[9 empty] | SAU2 16 | 168CH73
[9 empty] | SAU2 17 | GYPWD53
[9 empty] | SAU2 7 | 368CH73
[9 empty] | SAU2 8 | 378CH73
[9 empty] | SAU2 9 | D58CH73
[9 empty] | SAU2 1 | JYPWD53
[9 empty] | SAU2 10 | HYPWD53
[9 empty] | SAU2 2 | F58CH73
[9 empty] | SAU2 3 | 268CH73
[9 empty] | SAU2 11 | J68CH73
[9 empty] | SAU2 12 | 568CH73

## Validation2
Service_Tag | iDrac_IP | NIC1 | NIC2 | NIC3 | NIC4

## Sheet5 (hidden)
Done (Ruti) | Open | Generic
Done(Amit) | Close | Specific
Done (Eliran)
Done (Daniel)
Done
Fail
N/A
Open Issue
Partial